## Scrum Timeline
SCRUM TIMELINE
| Week Number | Tasks
| 13 | Workshops
| 14 | Workshops
| 15 | Workshops
| 16 | Outline Project Prototype | All Team
| 17 | Workshops
| 18 | Workshops
| 19 | Workshops
| 20 | Complete Front-End (1st Draft) | Jehan, Richard, Alfred
Sprint 1 | EV1 | Front-End (2nd Draft) | Jehan, Richard, Alfred
|  | Back-End - Create Database | Imran, Arthur
Sprint 2 | EV2 | Write Questions for Quiz | All Team
|  | Populate Database with Questions | Imran, Arthur
Sprint 3 | EV3 | Server-Side Setup & Link Front/Back-End | All Team
Sprint 4 | 21 | Feedback/Unit Testing | All Team
Sprint 5 | 22 | Report - Context & Background Research | All Team
Sprint 6 | 23 | Report - Results & Evaluation | All Team

## Kanban Timeline
Week Number | Tasks: Technical | Tasks: Documentation
EV2 Review | Learning MERN Stack
EV3 | Learning MERN Stack
21 | Learning MERN Stack
22 | Implement backend, populate database | Research for the report
23 | Link database to Frontend via API and start desigining front end | Planning documentation and begin writing the report
24 | Final CSS formatting of the web app - submit | Finish writing report and formatting - submit